## Prioritization
Feature Name | Description | Reach | Impact | Confidence | Effort | RICE Score | MVP | Rationale
Generate video captions | Use a third-party speech-to-text (STT) AI model to transcribe the narration from the video's audio channel. | 5 | 5 | 5 | 2 | 62.5 | No | Although captions are useful for accessibility, they are not essential to the core functionality of the MVP. This feature can be added post-launch to enhance accessibility.
Publish to TastyTube | Format the completed video to TastyTube specifications, prepopulate video metadata (e.g., title, description, recipe), and enable single-tap publishing to the site. | 5 | 5 | 5 | 2 | 62.5 | No | Enabling single-tap publishing to TastyTube, our primary platform, is essential for user adoption. It streamlines the sharing process for home chefs, making it effortless to distribute their content to a large audience.
Generate video title, description, and recipe summary | Use a third-party LLM to summarize video caption text into the following chunks: | 5 | 5 | 5 | 2 | 62.5 | Yes | Automatically generating titles, descriptions, and summaries saves content creators significant time and ensures consistent, SEO-optimized metadata, improving discoverability.
Create Recipe Library | Use the app to produce 5-8 high-quality recipe videos that demonstrate the capabilities of the app. | 3 | 4 | 5 | 2 | 30 | No | Showcasing high-quality recipe videos produced with the app demonstrates its capabilities and provides inspiration. This helps attract new users and accelerates adoption by offering practical examples.
Publish to YouVideo | Format the completed video to YouVideo specifications, prepopulate video metadata (e.g., title, description, recipe), and enable single-tap publishing to the site. | 4 | 4 | 5 | 3 | 26.6667 | No | While expanding to other platforms is valuable, focusing on TastyTube in the MVP allows us to concentrate resources on perfecting the core experience before scaling.
Publish to TikTak | Format the completed video to TikTak specifications, prepopulate video metadata (e.g., title, description, recipe), and enable single-tap publishing to the site. | 4 | 4 | 5 | 3 | 26.6667 | No | Similar to YouVideo, integration with additional platforms can be added post-MVP. Prioritizing TastyTube ensures we deliver a high-quality experience to our primary user base first.
Translate into other languages | Use a third-party LLM to translate text between the top 10 most commonly spoken languages in the TastyTube audience. | 3 | 3 | 5 | 2 | 22.5 | No | Translating content into multiple languages broadens our reach to a global audience. Utilizing a third-party LLM makes this feature low effort while significantly increasing impact.
Specify dataset | Retrieve from the TastyTube database the most popular 1,000 videos that meet the following criteria: | 2 | 4 | 5 | 2 | 20 | Yes | Defining the most relevant dataset ensures that AI models are trained on high-quality data, leading to better performance and more accurate video processing.
Create app to edit the clips and text | Create a mobile app for at least one of the major platforms. | 5 | 5 | 4 | 5 | 20 | Yes | The app is a crucial interface for users to interact with the platform, allowing them to edit and refine video clips with ease. Without this feature, users will not be able to create or polish their content.
Conduct usability testing | Test the MVP with target users, to identify any blockers and ideas for refinement prior to launch. | 2 | 4 | 4 | 2 | 16 | Yes | Usability testing helps identify pain points in the user experience and ensures the final product aligns with user needs. It’s critical for ensuring that the app meets user expectations at launch.
Publish to Fastgram | Format the completed video to Fastgram specifications, prepopulate video metadata (e.g., title, description, recipe), and enable single-tap publishing to the site. | 3 | 3 | 5 | 3 | 15 | No | Expanding to Fastgram is beneficial but not critical for the initial release. Focusing on one platform reduces complexity and speeds up the time to market.
Build ML model to classify recipe steps | Using the labeled training dataset, build a machine learning model to automate the process of classifying which cooking step the chef is performing in each clip. | 3 | 5 | 4 | 5 | 12 | No | While automating recipe step classification is valuable, it is not essential for the initial MVP. This feature can be postponed to a future iteration without impacting the core functionality of the app.
Build ML model to clip video into individual steps | Using the labeled training video dataset, build a machine learning model to automate the process of separating a raw recipe video into individual clips for each step in the recipe. | 3 | 5 | 4 | 5 | 12 | Yes | This model automates video segmentation, significantly reducing the manual effort required from content creators, which is key to driving adoption of the platform.
Conduct exploratory user research | To inform the MVP, observe 8-12 home chef content creators to understand their most common workflows for cooking, making videos, and social engagement. | 2 | 4 | 4 | 3 | 10.6667 | Yes | Understanding user workflows and pain points is essential for developing features that truly meet their needs. This research will ensure the app provides value and usability at launch.
Select and instruct labeling team | First, figure out how many human annotators you will need to complete the work in the required timeframe. | 1 | 3 | 5 | 2 | 7.5 | Yes | Efficient labeling requires human input. Selecting and instructing a team of annotators ensures data is prepared in a timely manner for training machine learning models.
Build Extensions API | Create a standardized, modular method for third-party developers to extend the app's functionality. | 2 | 3 | 4 | 4 | 6 | No | Providing an API for third-party developers is a valuable long-term strategy but not essential for the MVP. Focusing on core functionality first ensures a solid foundation before opening up for extensions.
Prepare data: Split videos into clips | In order to train a Machine Learning model that can automatically identify distinct cooking steps and split raw video into step-by-step clips, you'll need to have the dataset manually split into individual videos, one for each step in a recipe. | 1 | 4 | 5 | 4 | 5 | Yes | Segmenting videos into smaller, step-by-step clips is necessary for training AI models that help users create professional cooking videos quickly and easily.
Prepare data: Apply labels | In order to train a Machine Learning model to automatically identify the cooking step shown in a video, you'll need a human team to manually watch each video and apply labels to classify the following characteristics: | 1 | 4 | 5 | 5 | 4 | Yes | Manual labeling of data is essential for training accurate AI models. Without labeled data, the core functionality of recipe classification and video splitting cannot be developed.
MVP
Reach: 1 = large reach, 5 = large reach
Impact: 1 = small impact, 5 = large impact
Confidence: 1 = unlikely to meet objectives, 5 = highly likely to meet objectives
Effort: 1 = small amount of resources required, 5 = large amount of resources required

## MVP Roadmap
Feature Name | Sequence | # of Sprints | Team Resources | Dependencies | Technical Skills OpenSource | Technical Skills AWS | Technical Skills Azure | Technical Skills Google
Conduct exploratory user research | 1 | 1 | UX Researchers, Product Manager, Senior Sponsors, Legal | None | Survey tools, User research frameworks | None | None | None
Specify dataset | 2 | 1 | Data Engineers, Product Manager | Conduct exploratory user research | SQL, Python, Pandas | Amazon S3 | Azure Data Lake | Google Cloud Storage
Select and instruct labeling team | 3 | 1 | Data Annotators, Labeling Manager, Product Manager | Specify dataset | None | None | None | None
Prepare data: Split videos into clips | 4 | 2 | Data Engineers, Product Manager | Select and instruct labeling team | Python, FFmpeg | Amazon S3, AWS Lambda | Azure Data Lake, Azure Functions | Google Cloud Storage, Google Functions
Prepare data: Apply labels | 5 | 2 | Data Engineers, Labeling Team, Product Manager | Split videos into clips | SQL, Python, Labeling frameworks | Amazon SageMaker Ground Truth | Azure Machine Learning | Google Cloud AutoML
Build ML model to clip video into individual steps | 6 | 3 | Data Scientists, ML Engineers, Product Manager | Specify dataset, Apply labels | Python, TensorFlow, PyTorch, OpenCV | Amazon SageMaker | Azure Machine Learning | Google AI Platform
Create app to edit the clips and text | 7 | 4 | Mobile Developers, UI/UX Designers, Product Manager, Legal | Build ML model to clip video | React Native, Flutter | AWS Amplify | Azure App Service | Firebase
Generate video title, description, and recipe summary | 8 | 1 | Software Engineers, NLP Specialists, Product Manager | Create app to edit the clips and text | Python, NLTK, spaCy | Amazon Comprehend | Azure Text Analytics | Google Natural Language API
Conduct usability testing | 9 | 1 | UX Researchers, QA Testers, Product Manager | Create app to edit the clips and text | Usability testing tools | None | None | None
Sprint Cycle- 2-weeks